# ARTISTE OF THE YEAR PROJECT PROPOSAL

## PROJECT TITLE

SAY NO TODAY - Secure Her Tomorrow
A Region-Wide Girl Child Drug Abuse Awareness & Financial Empowerment Tour

## ARTISTE

Muslihat Mchelvert
Female Artiste | Upper West Region

## HEADLINE PROJECT SPONSOR

Wa Cooperative Credit Union (WACCU)

## ORGANISERS & MEDIA PARTNER

Upper West Progress Music Awards (UPPMA) 
Powered by Radio Progress

## PROJECT DURATION

12 Months (One Calendar Year)

PROJECT OVERVIEW:

SAY NO TODAY is a one-year, region-wide social impact project designed to address drug abuse among the girl child, while promoting financial discipline, savings culture, and cooperative membership through Wa Cooperative Credit Union (WACCU). Using music, advocacy, school and community engagements, and the project will reach all districts in the Upper West Region.

## PROJECT GOAL

## To reduce drug abuse among adolescent girls while promoting financial literacy, savings culture, and positive lifestyle choices across the Upper West Region.

## PROJECT OBJECTIVES

*To educate girls and young women on the dangers of drug abuse and peer pressure.

*To promote savings culture and cooperative membership through WACCU.

*To use music and radio as tools for behavioral change.

*To increase Muslihat Mchelvert’s visibility and fan base across all districts.

*To project Radio Progress and PRUMAS as socially responsible institutions

## KEY PROJECT ACTIVITIES

* Anti-drug abuse song production and promotion.

* Regional school and community outreach tour.

* WACCU financial education and membership mobilisation.

* Radio Progress media advocacy.

* Creative empowerment sessions.

PROJECT COORDINATION & MANAGEMENT:

The project will be overseen by a dedicated Project Coordinator responsible for planning, implementation, stakeholder engagement, reporting, and liaison between the artiste, WACCU, Radio Progress, schools, and community leaders. Supporting volunteers and district focal persons will assist during outreach activities to ensure smooth execution across all districts.

## EXPECTED WACCU MEMBERSHIP MOBILISATION OUTPUT

Through the regional outreach and radio engagements, the project is expected to mobilize new members for WACCU, particularly among youth and women.

### Projected Membership Mobilizations by District

| District | Projected New Members |
| --- | --- |
| Wa Municipal | 150 |
| Wa East | 80 |
| Wa West | 80 |
| Nadowli–Kaleo | 70 |
| Daffiama–Busie–Issa | 70 |
| Jirapa Municipal | 100 |
| Lambussie | 60 |
| Lawra Municipal | 100 |
| Nandom Municipal | 100 |
| Sissala East | 70 |
| Sissala West | 70 |

Total Projected New Members: 950

COMMUNITY LEADERS ENGAGEMENT & APPRECIATION:

To encourage community ownership and support, the project will recognize traditional leaders, opinion leaders, and education stakeholders who support the outreach activities. This will include:

* Presentation of branded appreciation certificates.

* Distribution of symbolic souvenirs (e.g. branded cloth, notebooks, or plaques).

* Public acknowledgement during community forums and radio mentions.

## ROLE OF WA COOPERATIVE CREDIT UNION (WACCU)

WACCU will:

*Fully finance the cash component of the project.

*Provide a project vehicle for regional movement.

*Take responsibility for fueling throughout the project period.

*Use the project as a platform to

*Mobilize new members

*Educate the public on its products

*Deepen its community impact

## ROLE OF RADIO PROGRESS

*Serve as the main media partner.

*Provide continuous publicity and airtime.

*Promote the awards scheme as impact-driven.

*Document and broadcast project outcomes.

## PROJECT BUDGET (GHS)

### Cash Component

| NO; ITEM; DESCRIPTION; COST (GHS). 1; Song Production; Recording, mixing & mastering; 2,500. 2; Artwork, PR, & Promotion; Digital promotion & design; 5.000. 3; Advocacy Music Video; Recording of music video; 3,000. 4; Regional Outreach Logistics; School & community activities; 4,000. 5; Girl Child Mentorship; Girl Child Mentorship Session; 3,500. 6; Radio Programs & Campaign; Jingles creation and air play; 2.500. 7; IEC Materials; Flyers & banners (branded); 3,500. 6; Creative Empowerment Clinics; Materials & facilitation; 2,000. 7; Media Engagement; Radio interviews & publicity; 3,000. 8; Documentation & Reporting; Photos, videos, reporting; 3,700. 9; Project Coordination; Planning & supervision; 3,800. 10; Community Leaders Engagement; Community leaders and gate keepers; 1,500. 11; Monitoring; Monitoring and evaluation team; 2,000. 12; Contingency; 4,000. |  |  |
| --- | --- | --- |

### TOTAL CASH BUDGET: GHS 44,000

### IN-KIND SUPPORT (NON-CASH)

*Project vehicle for all regional movements

*Full fueling for outreach activities

*Vehicle and material branding

*Staff support for membership education

## EXPECTED OUTCOMES

*Increased awareness on drug abuse among girls across the region.

*Improved financial literacy and savings mindset.

*Increased WACCU membership and brand visibility.

*Strong regional fan base for Muslihat Mchelvert.

*Enhanced public confidence in Radio Progress and UPPMA.

## SUSTAINABILITY

## *The advocacy song will continue to be used beyond the project year.

*Radio content remains accessible for future education.

*WACCU maintains long-term engagement with beneficiaries.

## CONCLUSION

SAY NO TODAY — Secure Her Tomorrow demonstrates how the Artiste of the Year title can be transformed into a platform for social change, financial empowerment, and community development. With the support of Wa Cooperative Credit Union and Radio Progress, Muslihat Mchelvert is well-positioned to deliver a project that impacts lives across the Upper West Region.